### Project Schedule

# Task							Milestones/Deliverables		Dur	Start		Finish

## Project Awarded											1d	Mon 1/20/03	Mon 1/20/03

## SOW & Approvals & Assets Delivered				B22 Deliverable				3d	Wed 1/22/03	Fri 1/24/03

SOW delivered											1d	Wed 1/22/03	Wed 1/22/03

Review and Approval by WDI of SOW									2d	Thu 1/23/03	Fri 1/24/03

## Delivery of Assets						WDI Deliverable				5d	Mon 1/20/03	Fri 1/24/03

## Kick Off Meetings						Full B22 & WDI Team			2d	Wed 1/22/03	Thu 1/23/03

## Technical Specifications Defined				Full Team Deliverable			2d	Thu 1/23/03	Fri 1/24/03

Technical Specifications Review Meeting								1d	Thu 1/23/03	Thu 1/23/03

Hosting Specs Defined										1d	Fri 1/24/03	Fri 1/24/03

Development Specs Defined										1d	Fri 1/24/03	Fri 1/24/03

DOL and Developer Tools Defined									1d	Fri 1/24/03	Fri 1/24/03

Testing Specs Defined										1d	Fri 1/24/03	Fri 1/24/03

## Master Schedule	 					Milestone 1: B22 Deliverable		5d	Mon 1/27/03	Fri 1/31/03

## Site Design Look & Feel					Milestone 1				10d	Mon 1/27/03	Fri 2/7/03

Creative Review Meetings					Full B22 & WDI Team			2d	Mon 1/27/03	Tue 1/28/03

Site Design Document					Milestone 1: B22 Deliverable			10d	Mon 1/27/03	Fri 2/7/03

## Initial Comps for Home Page & Spaceflight Experience		Milestone 1: B22 Deliverable		7d	Wed 1/29/03	Thu 2/6/03

Build Comps of Home Page & Spaceflight Experience							5d	Wed 1/29/03	Tue 2/4/03

Comp Review by WDI										2d	Wed 2/5/03	Thu 2/6/03

## Initial Comps for Storyboard of Intro Animation			Milestone 1: B22 Deliverable		4d	Wed 1/29/03	Mon 2/3/03

Storyboard Review by WDI										2d	Wed 1/29/03	Thu 1/30/03

Storyboard Changes by Developer									2d	Fri 1/31/03	Mon 2/3/03

## Page & Activity Design					Milestone 2				21d	Tue 2/4/03	Tue 3/4/03

## Final Build Home Page & Spaceflight Experience		Milestone 2: B22 Deliverable		7d	Fri 2/7/03		Mon 2/17/03

Revisions & Build of Home Page & Spaceflight Experience							6d	Fri 2/7/03		Fri 2/14/03

Revision & Build Review by WDI									1d	Mon 2/17/03	Mon 2/17/03

## Final Build of Intro Animation				Milestone 2: B22 Deliverable		6d	Tue 2/4/03	Tue 2/11/03

Animation Build											5d	Tue 2/4/03	Mon 2/10/03

Animation Build Review by WDI									1d	Tue 2/11/03	Tue 2/11/03

## Initial Comps Top Level Section Pages			Milestone 2: B22 Deliverable		7d	Wed 2/12/03	Thu 2/20/03

Build Comps of What Is Mission Space, Train at the Lab Pages						5d	Wed 2/12/03	Tue 2/18/03

Comp Review by WDI										2d	Wed 2/19/03	Thu 2/20/03

## Initial Comps Sub-Section Pages				Milestone 2: B22 Deliverable		8d	Fri 2/21/03	Tue 3/4/03

Build Comps of The Rocket, Capsule, Mission: SPACE Race, Expedition Mars, Postcards from Space, Space Base 	6d	Fri 2/21/03	Fri 2/28/03

Comp Review by WDI										2d	Mon 3/3/03	Tue 3/4/03

## Initial Comps Activities					Milestone 2: B22 Deliverable		8d	Mon 2/10/03	Wed 2/19/03

Build Comps of Send A Postcard Activity, Interactive Exploration of Rocket & Capsule				6d	Mon 2/10/03	Mon 2/17/03

Comp Review by WDI										2d	Tue 2/18/03	Wed 2/19/03

## Page & Activity Design Part 2				Milestone 3				30d	Fri 2/21/03	Thu 4/3/03

## Final Build of What Is Mission Space & Train at the Lab Pages	Milestone 3: B22 Deliverable		8d	Fri 2/21/03	Tue 3/4/03

Revisions & Build of What Is Mission Space and Train at the Lab Pages					6d	Fri 2/21/03	Fri 2/28/03

Revision & Build Review by WDI									2d	Mon 3/3/03	Tue 3/4/03

## Final Build Sub-Section Pages				Milestone 3: B22 Deliverable		10d	Mon 3/3/03	Fri 3/14/03

Revisions & Build of Train at the Lab Section pages & Spaceflight Experience Pages				7d	Mon 3/3/03	Tue 3/11/03

Revision & Build Review by WDI									3d	Wed 3/12/03	Fri 3/14/03

## Final Build Activities					Milestone 2: B22 Deliverable		16d	Mon 2/24/03	Mon 3/17/03

Build of Send A Postcard Activity, Interactive Exploration of Rocket & Capsule					14d	Mon 2/24/03	Thu 3/13/03

Review by WDI											2d	Fri 3/14/03	Mon 3/17/03

## Initial Comps Top Level Section Pages			Milestone 3: B22 Deliverable		8d	Wed 2/26/03	Fri 3/7/03

Build Comps of Astronaut Experience, Downloads, Astronaut Candidate Page (My Page)				6d	Wed 2/26/03	Wed 3/5/03

Comp Review by WDI										2d	Thu 3/6/03	Fri 3/7/03

## Initial Comps Sub-Section Pages				Milestone 3: B22 Deliverable		7d	Tue 3/4/03	Wed 3/12/03

Build Comps of 4 Capsule Roles, Firsts in Space, Downloads sub-section pages					5d	Tue 3/4/03	Mon 3/10/03

Comp Review by WDI										2d	Tue 3/11/03	Wed 3/12/03

## Initial Comps Activities					Milestone 3: B22 Deliverable		10d	Fri 3/21/03	Thu 4/3/03

Build Comps of Capsule Sequencing, Virtual Tour, Art Gallery						8d	Fri 3/21/03	Tue 4/1/03

Comp Review by WDI										2d	Wed 4/2/03	Thu 4/3/03

## Initial Comps Log-In/Reg and Schematics of Registration & Points System	Milestone 3: B22 Deliverable	11d	Thu 3/13/03	Thu 3/27/03

Build Comps of Log-In/Reg Pages & Schematic of Registration & Points System 					8d	Thu 3/13/03	Mon 3/24/03

Comp Review by WDI										3d	Tue 3/25/03	Thu 3/27/03

## Alpha Stage						Milestone 4				34d	Mon 3/10/03	Thu 4/24/03

## Final Build of Virtual Tour Activity & Capsule Sequencing Game	Milestone 4: B22 Deliverable		16d	Thu 4/3/03	Thu 4/24/03

Revisions & Build of Virtual Tour Activity & Capsule Sequencing Game						14d	Thu 4/3/03	Tue 4/22/03

Revision & Build Review by WDI									2d	Wed 4/23/03	Thu 4/24/03

## Final Build Sub-Section Pages				Milestone 4: B22 Deliverable		10d	Mon 3/10/03	Fri 3/21/03

Revisions & Build of Astronaut Experience section, Downloads section, Astronauat Candidate Page (My Page)		7d	Mon 3/10/03	Tue 3/18/03

Revision & Build Review by WDI									3d	Wed 3/19/03	Fri 3/21/03

## Initial Comps Downloads & Mission Patches			Milestone 4: B22 Deliverable		11d	Thu 3/20/03	Thu 4/3/03

Build Comps of Wallpapers, Screensavers, Desktops, Sounds/Clips etc.					9d	Thu 3/20/03	Tue 4/1/03

Comp Review by WDI										2d	Wed 4/2/03	Thu 4/3/03

## Integration and Implementation of Navigational Elements 	Milestone 4: B22 Deliverable		3d	Fri 4/4/03		Tue 4/8/03

Integration with DOL chrome		3d	Fri 4/4/03	Tue 4/8/03

## Alpha Integration Log-In/Reg and Points System with GOREG	Milestone 4: B22 Deliverable		9d	Wed 4/9/03	Mon 4/21/03

Integration with DOL's GOREG System									8d	Wed 4/9/03	Fri 4/18/03

Review by WDI											1d	Mon 4/21/03	Mon 4/21/03

## Testing, Integration & Launch				Milestone 5				36d	Fri 4/4/03		Fri 5/23/03

## Final Build Downloads & Mission Patches			Milestone 5: B22 Deliverable		9d	Fri 4/4/03		Wed 4/16/03

Build of Wallpapers, Screensavers, Icons, Desktops, Sounds/Clips etc.						7d	Fri 4/4/03		Mon 4/14/03

Review by WDI											2d	Tue 4/15/03	Wed 4/16/03

Initial Comps Astronaut Screenmate, Vacation Countdown Clock, Astronaut Personality Quiz, and Desktop Cursors

Milestone 5: B22 Deliverable		16d	Thu 4/17/03	Thu 5/8/03

Build Comps of Astronaut Screenmate, Vacation Countdown Clock, Astronaut Personality Quiz, and Desktop Cursors

14d	Thu 4/17/03	Tue 5/6/03

Comp Review by WDI										2d	Wed 5/7/03	Thu 5/8/03

## B22 Internal QA and Testing					Milestone 5: B22 Deliverable		14d	Mon 4/21/03	Thu 5/8/03

## Integration and Testing with DOL/WDPRO 			Milestone 5: WDI & B22			10d	Fri 5/9/03		Thu 5/22/03

Testing on Sandbox											10d	Fri 5/9/03		Thu 5/22/03

Integration of Hitbox Code 										5d	Mon 5/12/03	Fri 5/16/03

Bug Fixes												5d	Fri 5/16/03	Thu 5/22/03

## Burn entire site to CD & Launch Final Site			Milestone 5: B22 Deliverable		2d	Thu 5/22/03	Fri 5/23/03

## Phase 2 Rollout						Milestone 6				36d	Fri 5/9/03		Fri 6/27/03

Final Build Astronaut Screenmate, Vacation Countdown Clock, Astronaut Personality Quiz, and Desktop Cursors

Milestone 6: B22 Deliverable		27d	Fri 5/9/03		Mon 6/16/03

Build of Astronaut Screenmate, Vacation Countdown Clock, Astronaut Personality Quiz, and Desktop Cursors		20d	Fri 5/9/03		Thu 6/5/03

Review by WDI											7d	Fri 6/6/03		Mon 6/16/03

Integration and Testing of 3rd Party Games: X2 Landing Challenge, Mission Space Race Online, Expedition Mars

Milestone 6: WDI & B22			19d	Fri 5/30/03	Wed 6/25/03

Testing on Sandbox											14d	Fri 5/30/03	Wed 6/18/03

Integration of Hitbox Code 										5d	Fri 6/6/03		Thu 6/12/03

Bug Fixes												5d	Thu 6/19/03	Wed 6/25/03

## B22 Internal QA and Testing					Milestone 6: B22 Deliverable		3d	Mon 6/23/03	Wed 6/25/03

## Burn entire site to CD & Launch Final Site			Milestone 6: B22 Deliverable		2d	Wed 6/25/03	Thu 6/26/03

## Documentation Follow-Up					Milestone 6: B22 Deliverable		3d	Wed 6/25/03	Fri 6/27/03